## Product BackLog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a user, I want to create an account so that I can securely access the AI Decision Hub. | Must | Database, Authentication | me | Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want to log in securely so that I can access my conversations and decisions. | Must | Authentication | me | Completed
Sprint 1 | Sprint 1 | US03 | As a user, I want to submit a decision-related query so that the system can analyze it. | Must | Backend API | me | Completed
Sprint 1 | Sprint 1 | US04 | As a user, I want the Coordinator Agent to identify the tasks required for my query. | Must | LLM, Agent Workflow | me | Completed
Sprint 1 | Sprint 1 | US05 | As a user, I want specialized agents to perform different tasks such as research, analysis and decision making. | Must | Coordinator Agent | me | Completed
Sprint 1 | Sprint 1 | US06 | As a user, I want agents to share information through a common workflow state. | Must | Agent Workflow | me | Completed
Sprint 1 | Sprint 1 | US07 | As a user, I want the system to use external tools when required to solve my query. | Must | Tool APIs | me | Completed
Sprint 1 | Sprint 1 | US08 | As a user, I want my previous conversations to be stored so that I can access them later. | Should | Database | me | Completed
Sprint 1 | Sprint 1 | US09 | As a user, I want the system to generate a final recommendation based on the information collected by the agents. | Must | Analysis Agent, Decision Agent | me | Completed
Sprint 1 | Sprint 1 | US10 | As a user, I want to see the status and progress of my AI workflow. | Should | Agent Workflow, Logging | me | Completed
Sprint 1 | Sprint 1 | US11 | As an administrator, I want to monitor agent executions, failures and response times. | Should | Logging, Database | me | Completed
Sprint 1 | Sprint 1 | US12 | As a user, I want the application to handle API and agent failures gracefully. | Must | Error Handling | me | Completed
Sprint 1 | Sprint 1 | US13 | As a user, I want a responsive web interface for interacting with the AI Decision Hub. | Must | React/HTML/CSS/JS | me | Completed
Sprint 1 | Sprint 1 | US14 | As a user, I want the application to be deployed so that it can be accessed remotely. | Must | Deployment | me | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Team Member | Activity | Status | Estimate
US01 | T01 | Design user registration form and validation | Team Member 1 | Frontend | Completed | 3
US01 | T02 | Implement user registration API | Team Member 1 | Backend | Completed | 4
US02 | T03 | Implement login and authentication | Team Member 1 | Backend | Completed | 5
US03 | T04 | Create decision query interface | Team Member 2 | Frontend | Completed | 4
US03 | T05 | Create API endpoint for decision requests | Team Member 2 | Backend | Completed | 4
US04 | T06 | Implement Coordinator Agent | Team Member 2 | AI/Agent | Completed | 7
US05 | T07 | Implement Planning Agent | Team Member 3 | AI/Agent | Completed | 5
US05 | T08 | Implement Research Agent | Team Member 3 | AI/Agent | Completed | 6
US05 | T09 | Implement Analysis Agent | Team Member 4 | AI/Agent | Completed | 6
US05 | T10 | Implement Decision Agent | Team Member 4 | AI/Agent | Completed | 6
US06 | T11 | Define shared workflow state | Team Member 3 | Backend | Completed | 4
US07 | T12 | Integrate weather API/tool | Team Member 4 | API Integration | Completed | 4
US07 | T13 | Integrate calculator/budget tool | Team Member 4 | API Integration | Completed | 3
US08 | T14 | Store conversation history | Team Member 5 | Database | Completed | 5
US09 | T15 | Implement final decision generation | Team Member 4 | AI/Agent | Completed | 5
US10 | T16 | Create workflow execution status UI | Team Member 6 | Frontend | Completed | 5
US11 | T17 | Implement agent execution logging | Team Member 6 | Monitoring | Completed | 5
US11 | T18 | Create monitoring dashboard | Team Member 6 | Frontend | Completed | 6
US12 | T19 | Add exception and API error handling | Team Member 7 | Backend | Completed | 5
US12 | T20 | Add timeout and retry handling | Team Member 7 | Backend | Completed | 4
US13 | T21 | Improve dashboard and responsive UI | Team Member 5 | Frontend | Completed | 6
US14 | T22 | Configure production environment | Team Member 7 | Deployment | In Progress | 5
US14 | T23 | Deploy frontend and backend | Team Member 7 | Deployment | In Progress | 6
US14 | T24 | Perform end-to-end deployment testing | Team Member 7 | Testing | Not Started | 4

## Stand up meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty deciding responsibilities of individual agents. | Defined responsibilities for Coordinator, Planning, Research, Analysis and Decision agents.
Sprint 1 | Day 2 | Agent workflow was not passing information correctly between stages. | Updated shared state structure and tested state transitions.
Sprint 1 | Day 3 | Weather API returned inconsistent results for some locations. | Added input validation and improved API request handling.
Sprint 1 | Day 4 | Frontend was not communicating with backend correctly. | Configured API endpoints and CORS settings.
Sprint 1 | Day 5 | Conversation history was not being persisted correctly. | Updated database storage and retrieval logic.
Sprint 1 | Day 6 | Some agent executions were taking too long. | Added execution timing logs and reduced unnecessary agent calls.
Sprint 1 | Day 7 | Authentication errors occurred during API requests. | Fixed token handling and protected API endpoints.
Sprint 1 | Day 8 | UI did not clearly show workflow progress. | Added workflow status indicators.
Sprint 1 | Day 9 | Agent failure was not handled gracefully. | Added exception handling and controlled retries.
Sprint 1 | Day 10 | Deployment configuration issues. | Updated environment variables and deployment configuration.

## Retrospection
SL | Sprint | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | Team Member 1 | Start testing authentication earlier. | Stop waiting until the end to integrate frontend and backend. | Continue maintaining clear API contracts. | Added authentication test cases before integration.
2 | Sprint 1 | Team Member 2 | Start documenting agent responsibilities before implementation. | Stop changing agent responsibilities frequently. | Continue testing Coordinator routing. | Created agent responsibility documentation.
3 | Sprint 1 | Team Member 3 | Start testing shared state after every workflow stage. | Stop relying only on final output for debugging. | Continue modular agent development. | Added state validation after agent execution.
4 | Sprint 1 | Team Member 4 | Start testing external APIs with failure cases. | Stop assuming APIs will always respond successfully. | Continue integrating reusable tools. | Added timeout and error handling.
5 | Sprint 1 | Team Member 5 | Start integrating UI with backend earlier. | Stop developing frontend independently for too long. | Continue improving usability. | Connected major UI components to backend APIs.
6 | Sprint 1 | Team Member 6 | Start tracking agent execution metrics earlier. | Stop relying only on console logs. | Continue working on monitoring. | Added structured execution logging.
7 | Sprint 1 | Team Member 7 | Start deployment testing before the final stage. | Stop treating deployment as a last-minute activity. | Continue maintaining backend stability. | Created deployment checklist and tested environment configuration.